## Change Log
ABC Company Production Database Project Change Log
ID | Platform | Code | Description | Comments | Status | Date
001 | GUI | ADD | usereditform.php | UI page for basic user to request changes to database rows. | Complete | 2017-07-31
002 | Programming | ADD | usereditsubmit.php | Converts form data from user edit form to PHP variables. Pushes SQL command to pull selected prodID and insert form variables to mEditList in Production database for manager approval. | Complete | 2017-08-19
003 | Database | ADD | mEditList | Add table for edit requests from users. | Complete | 2017-08-04
004 | Project | DROP | Custom Reports | Work expands beyond scope of project. | Complete | 2017-08-01
005 | GUI | ADD | userentrydata.php | UI page for users to review all their stored entries in the database. | Complete | 2017-08-19
006 | Programming | ADD | userentrydb.php | Pulls user entered data from database and displays on GUI for user. | Complete | 2017-08-19
007 | Project | CHANGE | Manager Portal | Due to project scope, manager portal will be built into design, but will not have all management functions per requests. | Complete | 2017-08-01
008 | GUI | ADD | mgredit.php | UI page for managers to review edit requests. | Complete | 2017-08-19
009 | GUI | ADD | mgradmindashboard.php | UI dashboard that allows managers to access functions to add, alter (correct data or change admin level), or remove users within app. | Complete | 2017-08-19
010 | Programming | ADD | mgradduser.php | Programming to add user to userAcc table. | Complete | 2017-08-19
011 | GUI | ADD | mgradmin.php | GUI page for managers to review edit requests. | Complete | 2017-08-19
012 | Programming | ADD | mgrdb.php | Programming to connect manager to database | Complete | 2017-08-19
013 | Programming | ADD | mgrdbalter.php | Programming to update completedTasks rows per user edit request. | Complete | 2017-08-19
014 | GUI | ADD | mgrdbdeleteuser.php | GUI to delete a user from the userAcc table. | Complete | 2017-08-19
015 | GUI | ADD | mgrdbedituser.php | GUI to edit a user from the userAcc table. | Complete | 2017-08-19
016 | Programming | ADD | mgrdeleteuser.php | Programming to delete a user from the userAcc table. | Complete | 2017-08-19
017 | Programming | ADD | mgrdisc.php | Log off function for manager portal. | Complete | 2017-08-19
018 | GUI | ADD | mgreditform.php | GUI form for managers to review and perform edit requests. | Complete | 2017-08-19
019 | Programming | ADD | mgredituser.php | Programming to edit user from the userAcc table. | Complete | 2017-08-19
020 | GUI | ADD | mgrportal.php | GUI manager main dashboard. | Complete | 2017-08-19
021 | GUI | ADD | mgrdbadduser.php | GUI to add user to userAcc table. | Complete | 2017-08-19
022
023
024
025
026
027
028
029
030
031
032
033
034
035
036
037
038
039
040
041
042
043
044
045
046
047
048
049

## File Log
ABC Company Production Database Project File Log
ID | Platform | Portal | Description | Relationship | Comments
001 | GUI | All | index.php |  | Initial page for user login -- doubles as manager log in. Sets user session.
002 | Programming | Basic | userdb.php |  | Programming for database connection using user credentials set on global session -- used by GUI pages for inline PHP SQL commands.
003 | GUI | Basic | userdbform.php | 002 | User form for entering production data into the database.
004 | Programming | Basic | userdbinput.php | 003 | Programming code for inserting production data into the database.
005 | Programming | Basic | userdisc.php |  | Programming code for ending session -- Log Out
006 | GUI | Basic | usereditform.php | 002 | User form for requesting changes to entered data in database.
007 | Programming | Basic | usereditsubmit.php | 006 | Programming to insert new data into manager table for edit review and approval.
008 | GUI | Basic | userentryreview.php | 002 | User page to view all entered data in the database table.
009 | GUI | Basic | userportal.php |  | User dashboard for selecting functions.
010 | Programming | Basic | usernav.php |  | Programming to return user to user dashboard.
011 | Programming | All | style.css |  | Universal style sheet.
012 | GUI | Manager | mgredit.php | 024 | UI page for managers to review edit requests.
013 | GUI | Manager | mgradmindashboard.php | 024 | UI dashboard that allows managers to access functions to add, alter (correct data or change admin level), or remove users within app.
014 | Programming | Manager | mgradduser.php | 025 | Programming to add user to userAcc table.
015 | GUI | Manager | mgradmin.php | 024 | GUI page for managers to review edit requests.
016 | Programming | Manager | mgrdb.php |  | Programming to connect manager to database
017 | Programming | Manager | mgrdbalter.php | 022 | Programming to update completedTasks rows per user edit request.
018 | GUI | Manager | mgrdbdeleteuser.php | 015 | GUI to delete a user from the userAcc table.
019 | GUI | Manager | mgrdbedituser.php | 015 | GUI to edit a user from the userAcc table.
020 | Programming | Manager | mgrdeleteuser.php | 015 | Programming to delete a user from the userAcc table.
021 | Programming | Manager | mgrdisc.php |  | Log off function for manager portal.
022 | GUI | Manager | mgreditform.php | 024 | GUI form for managers to review and perform edit requests.
023 | Programming | Manager | mgredituser.php | 019 | Programming to edit user from the userAcc table.
024 | GUI | Manager | mgrportal.php |  | GUI manager main dashboard.
025 | GUI | Manager | mgrdbadduser.php | 015 | GUI to add user to userAcc table.
026
027
028
029
030
031
032
033
034
035
036
037
038
039
040
041
042
043

## SQL Commands Log
ABC Company Production Database SQL Log
ID | Platform | File | Description | Required PHP | Comments
001 | GUI | userdbform.php | SELECT deptName FROM depts SELECT taskName FROM taskList |  | Selects data from tables to display into dropdown menus.
002 | Programming | userdbinput.php | INSERT INTO completedTask (userName, deptName, taskName, time, count, entryDate, Comment) VALUES ('$userName','$dept', '$taskName', '$time', '$count', '$date', '$comment') | session start(); $dept=$_POST['dept']; $count=$_POST['count']; $taskName=$_POST['task']; $time=$_POST['time']; $date=$_POST['date']; $userName=$_SESSION['username']; $password=$_SESSION['password']; $array = array($dept,$taskName,$count,$time,$date); $comment = implode(' > ',$array); | Uses variables from entered form data and parses into PHP variables. These variables are then used within the SQL command. Sesion is required to set username and password from log in screen.
003 | GUI | usereditform.php | SELECT * From completedTask WHERE userName='". $username ."' SELECT taskName FROM taskList ORDER BY taskName ASC SELECT reason FROM editReasons ORDER BY reason ASC | userdp.php session start(); $username=$_SESSION['username']; $date = date('Y-m-d') | Selects data from tables to display into dropdown menus. Allows user to select the data they have inserted into the database for edit requests.
004 | Programming | usereditsubmit.php | INSERT INTO mEditList (prodID, userName, deptName, taskName, time, count, entryDate, com1, com2) VALUES ('$entry','$userName','$deptName', '$taskName', '$time', '$count', '$date', '$comment1', '$comment2') | session_start(); $entry=$_POST['entry']; $deptName=$_POST['deptName']; $count=$_POST['count']; $taskName=$_POST['task']; $time=$_POST['time']; $date=$_POST['date']; $reason1=$_POST['reason1']; $reason2=$_POST['reason2']; $userName=$_SESSION['username']; $password=$_SESSION['password']; $array2 = array($reason1,$reason2); $array1 = array($entry,$deptName,$count,$taskName,$time,$date); $comment2 = implode(' + ',$array2); $comment1 = implode(' > ',$array1); | Enters updated data into a manager table for review through manager portal.
005 | GUI | userentryreview.php | SELECT * From completedTask WHERE userName='". $username ."' ORDER BY entryDate DESC | session_start(); $userName=$_SESSION['username']; | Pulls all user entered data into a dropdown for review.
006 | Programming | mgradduser.php | INSERT INTO userAcc (deptName, fName, lName, admin, userName) VALUES ('$deptName','$fName', '$lName', '$admin', '$user' | session_start(); $deptName=$_POST['deptName']; $fName=$_POST['fName']; $lName=$_POST['lName']; $user=$_POST['userName']; $admin=$_POST['admin']; settype ($admin, "integer"); | Adds user into the useAcc table.
007 | GUI | mgradmin.php | SELECT * From mEditList SELECT deptName FROM depts SELECT taskName FROM taskList ORDER BY taskName ASC |  | Pulls all user requests from mEditList table to display in a dropdown menu along with form for altering rows for users.
008 | GUI | mgrdatareports.php | SELECT * From completedTask ORDER BY entryDate DESC | <?php if($stmt=$conn->query("SELECT * From completedTask ORDER BY entryDate DESC")){?> <table class="data-table"> <caption class="title"></caption> <thead><tr><th>User</th><th>Dept</th><th>Task</th><th>Time</th><th>Count</th><th>Date</th></tr></thead><tbody> <?php while ($row = mysqli_fetch_array($stmt)) {echo '<tr><td>'.$row['userName'].'</td><td>'.$row['deptName'].'</td><td>'.$row['taskName'].'</td><td>'.$row['time'].'</td><td>'.$row['count'].'</td><td>'.$row['entryDate'].'</td></tr>'; }}?> | Pulls all entered data in the completedTask table.
009 | GUI | mgrdbadduser.php | SELECT deptName FROM depts |  | Selects data from tables to display into dropdown menus.
010 | Programming | mgrdbalter.php | UPDATE completedTask SET `deptName` = '". $deptName ."', `taskName` = '". $taskName ."', `time` = '". $time ."', `count` = '". $count ."', `entryDate` = '". $date ."', `Comment` = '". $comment ."' WHERE `prodID` = '". $prodID ."' DELETE FROM mEditList WHERE `prodID` = '". $prodID ."' | session_start(); $prodID=$_POST['entry']; $submit=$_POST['submit']; $deptName=$_POST['deptName']; $count=$_POST['count']; $taskName=$_POST['taskName']; $time=$_POST['time']; $date=$_POST['date']; $userName=$_SESSION['username']; $password=$_SESSION['password']; $array = array($deptName,$taskName,$count,$time,$date); $comment = implode(' > ',$array); settype ($prodID, "integer"); | Updates completedTask row for user or deletes the request on mEditList.
011 | GUI | mgrdbdeleteuser.php | SELECT * FROM userAcc |  | Selects data from tables to display into dropdown menus.
012 | GUI | mgrdbedituser.php | SELECT * FROM userAcc SELECT deptName FROM depts |  | Selects data from tables to display into dropdown menus.
013 | Programming | mgrdeleteuser.php | DELETE FROM userAcc WHERE `userName` = '". $user ."' | session_start(); $user=$_POST['userDelete']; | Deletes user from userAcc table.
014 | GUI | mgreditform.php | SELECT * From mEditList SELECT deptName FROM depts SELECT taskName FROM taskList ORDER BY taskName ASC |  | Selects data from tables to display into dropdown menus.
015 | Programming | mgredituser.php | UPDATE userAcc SET `deptName` = '". $deptName ."', `fName` = '". $fName ."', `lName` = '". $lName ."', `admin` = '". $admin ."', `userName` = '". $login ."' WHERE `userName` = '". $user ."' | session_start(); $deptName=$_POST['deptName']; $fName=$_POST['fName']; $lName=$_POST['lName']; $user=$_POST['userName']; $login=$_POST['user']; $admin=$_POST['admin']; settype ($admin, "integer"); | Updates row in the userAcc table to edit user information.
016
017
018
019
020
021
022
023
024
025
026
027
028
029
030
031
032
033
034
035
036
037
038
039
040
041
042
043

## Risk Log
ABC Company Production Database Project Risk Log
ID | Platform | Risk Type | Description | Level | Comments | Mitigation | Date | Manager | Resolved
001 | Scope | Functionality | Custom Reports | High | Manager request for functionality to customize generated reports. Production will expand beyond project timeline. | Recommend allocating to new project as is not high priority. | 2017-07-31 | RH | 2017-08-01
002 | GUI | Security | Admin Authorization | Low | Limited ability to determine authorization levels for application use based on server side user accounts. | Set user access level in userAcc table in database. Set authentication checks within programming codes. | 2017-07-31 | RH | 2017-08-01
003 | GUI | Seurity | Manager Portal | Medium | Program allows access to all pages for any user. | Set authentication checks within programming to route logged in user to respective portal. | 2017-07-31 | RH | 2017-08-01
004 | Programming | Security | Admin Authorization | Medium | Authentication checks need to be precise to prevent programming loops. | Simple inline PHP codes to check session status and admin level for redirect to respective portals. | 2017-07-31 | RH | 2017-08-13
005
006
007
008
009
010
011
012
013
014
015
016
017
018

## Feedback
ABC Company Production Database Feedback Log
ID | Platform | Requestor | Description | Comments | Scope
001 | Feature | Manager | Custom report queries. | ABC Company has database query software. | N
002 | Feature | Stakeholder | User data entry form. | Main purpose of application. | Y
003 | Function | Stakeholder | Export to excel for weekly data report. | Used for exporting data from database table for reporting work volume | N
004 | Feature | User | Non-refresh dropdown menus. | Users request a dropdown form that retains prior selected data. | N
005 | Function | Manager | Edit user entries to correct data. | Front-end function for editing user requested edits to entered data. | Y
006 | Security | IT Security | Access controls to prevent unauthorized access. | Authentication measures for users. | Y
007 | Security | IT Security | Administrative access controls. | Separation from basic and manager portals. | Y
008 | Function | Manager | Administrative tools for user controls. | Functions to add/edit/delete user access. | Y
009 | Feature | User | Split window to view entered data in database on data entry page. | Feature used to be able to view data already entered on the same page as the entry form to avoid duplication | N
010
011
012
013
014
015
016
017
018
019
020
021
022
023
024
025
026
027
028
029
030
031
032
033
034
035
036
037
038
039
040
041
042
043